## User Interface
PROGRESS REPORT
PAGE | % COMPLETE | DONE | REMARKS | PERSON-IN-CHARGE
Login / Register | 100% | 100%
Dashboard | 75% | 0% | Fix layout, match design with other pages
Project List | 0% | 0
Calendar of Activities | 75% | 0 | Fix layout, match design with other pages
Template Repository | 0% | 0
User List | 0% | 0
Registration Validation | 75% | 0 | Fix layout, match design with other pages
0
0
0
0

## Back end
PROGRESS REPORT
FUNCTIONS | USER STORY # | ITERATION | % COMPLETE | DONE | REMARKS | PERSON-IN-CHARGE
Login | 1 | 1 | 100% | 100% |  | Joseph Ongsingco
Register | 2 | 1 | 100% | 100% |  | Miguel Manalac
User Validation | 3 | 1 | 100% | 1 |  | Miguel Manalac
President informed of status Pre & Post reqs | 4 | 2 |  | 0
Document Repository | 5 | 2 |  | 0
Pre-activitiy Requirements Checklist | 6 | 2 |  | 0
Requirements checklist during event | 7 | 2 |  | 0
Accessing of Document Templates | 8 | 2 |  | 0
Project Head informs of Project Status | 9 | 2 |  | 0
Deadline reminders for project heads | 10 | 2 |  | 0
Post-activity Requirements Checlist | 11 | 2 |  | 0
Committee Head notified when tagged in COA | 12 | 2 |  | 0
View workload of officers | 13 | 2 |  | 0
Project Assigning in COA and notification | 14 | 2 |  | 0
Add Project in COA | 15 | 1 | 100% | 1 |  | Carlo Bautista
Notifications on updates in COA | 16 | 2 |  | 0
Pub Head notified of done Pre-act requirements stage of projects | 17 | 2 |  | 0
Logout | 18 | 1 | 100% | 1 |  | Joseph Ongsingco
Update project details in COA | 19 | 1 | 100% | 1 |  | Carlo Bautista

## Test Cases
PROGRESS REPORT
USER STORY | ITERATION | % COMPLETE | DONE | REMARKS | PERSON-IN-CHARGE
1 | 1 | 50% | 0% | Still to test | Ralph Chua
2 | 1 | 75% | 0% | Not yet done testing | Brandon Partosa
3 | 1 | 0% | 0 |  | Brandon Partosa
4 | 2 |  | 0
5 | 2 |  | 0
6 | 2 |  | 0
7 | 2 |  | 0
8 | 2 |  | 0
9 | 2 |  | 0
10 | 2 |  | 0
11 | 2 |  | 0
12 | 2 |  | 0%
13 | 2 |  | 0%
14 | 2 |  | 0%
15 | 1 | 0% | 0% |  | Edgar Dimanarig
16 | 2 |  | 0%
17 | 2 |  | 0%
18 | 1 | 50% | 0% | Still to test | Ralph Chua
19 | 1 | 50% | 0% | Still to test | Edgar Dimanarig

## Paperworks
PROGRESS REPORT
PAPER | % COMPLETE | DONE | REMARKS
Software System Specficiation | 100% | 100%
Project Plan | 100% | 100%
Entity-Relationship Model | 100% | 1
Class Diagram | 0% | 0 | To be done during Integration II
0
0
0
0
0
0
0